## Tabelle1
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Literature Review | bar: 22 to 24; 27 to 1; 6; 13; 20; 10; 17
Writing Project Proposal | bar: 22 to 24
Preparing Proposal Presentation | bar: 22 to 23
Setting up Programming Environment | bar: 22 to 23
Complete important RePast Tutorials | bar: 23 to 24; 27 to 28
Developing the Word-Building Ontology | bar: 24; 27
Developing the Environment | bar: 27 to 29
Developing Letter Resources | bar: 28 to 1
Developing Agents | bar: 29 to 1
Developing Demands | bar: 1; 4 to 7
Developing Supply Calculation | bar: 6 to 8; 11 to 14
Developing Communication | bar: 11 to 15; 18 to 22
Developing Resource Propagation | bar: 15; 18 to 22; 25 to 26
Developing Intelligence Parameters | bar: 21 to 22; 25 to 29
Preparing Progress Presentation | bar: 27 to 29
Experiments / Evaluation | bar: 28 to 29; 1 to 5; 8 to 11
Writing Thesis | bar: 4 to 5; 8 to 12; 15 to 19; 22 to 23
Preparing Final Presentation | bar: 23 to 25
Reading
Writing
Programming
Experiment / Evaluation